## Task_Table
% Complete | Name | Start | Finish | Resource Responsibility | Notes
0% | Business Continuity Planning
0% | COOP Administrative Tasks
0% | Determine if Agency has Microsoft Project Software, if not send exported copy of project plan as excel file for agency to update
0% | Pre-Exercise Activities
0% | Monthly Drill Meetings
0% | Schedule meetings with agency COOP Coordinator(s) & DEMA Continuity Coordinator (DEMA As Optional)
0% | Conduct meetings with agency COOP Coordinator(s) & DEMA Continuity Coordinator (DEMA As Optional)
0% | Determine exercise date
0% | Determine exercise location
0% | Determine Evaluators
0% | Logistics
0% | Schedule tour at Alternate/Drill Location (if applicable)
0% | Tour Alternate/Drill Location (if applicable)
0% | Review and confirm Alternate/Drill Location room specifications (if applicable)
0% | Review and confirm Alternate/Drill Location network/phone specifications (if applicable)
0% | Review and confirm parking availability (if applicable)
0% | Have technical resource identify necessary equipment (Laptop, Projector & Projection Screen) (if applicable)
0% | Identify both technical and basic office supplies (Flip Chart/White Board/Pens/Tablets) (if applicable)
0% | Agency Continuity Coordinator schedule date for equipment prepositioning (if applicable)
0% | Agency Continuity Coordinator ensure equipment is prepositioned at Alternate/Drill Location (if applicable)
0% | Agency Continuity Coordinator order needed supplies (if applicable)
0% | Agency Continuity Coordinator schedule equipment testing (if applicable)
0% | Technical resource conducts equipment testing (if applicable)
0% | Continuity Coordinator Document any findings from equipment testing (if applicable)
0% | Agency Communications
0% | Schedule Crisis Communication Training for Agency Plan Builders/Administrators
0% | Print/send Crisis Communication Training Guide for attendees
0% | Participate in Crisis Communication Training
0% | Provide Executive Level Management with exercise updates
0% | Coordinate preparation and distribution of communications to all organizational staff
0% | Review and modify agenda for day of exercise
0% | Schedule meeting with participants (mandatory) and managers (optional) to review roles and responsibilities
0% | Conduct meeting with participants (mandatory) and managers (optional) to review roles and responsibilities
0% | Conduct meeting with evaluators to review roles and responsibilities
0% | Pre-Test Preparation
0% | DTI provides agency with all COOP Drill template documents needed to support exercise
0% | Solicit resources for assessment of infrastructure requirements for each location
0% | Determine business unit groups participating in exercise
0% | Send calendar invite to all exercise participants and managers
0% | Request admins to tentatively block out Executive level staff calendars for exercise dates
0% | Send courtesy invite for exercise to DEMA representatives Mike O'Malley & Edward "Tony" Lee
0% | Send courtesy invite for exercise to DTI COOP Liaison and DTI Customer Engagement Specialist
0% | Solicit 1 Manager and 1 or more employees from each business unit to participate in exercise
0% | Determine scope of plan building needed to support exercise
0% | Ensure Business Unit Leaders review COOP plan content
0% | Agency CC updates COOP plan with changes based on Business Unit review
0% | Test Day Activities (these tasks will change based on objectives)
0% | Participant Registration & Sign In
0% | Test connectivity to systems at Alternate/Drill Location (Optional)
0% | Return Alternate/Drill Location area to original layout
0% | Conduct Hotwash
0% | Distribute and collect completed evaluations
0% | Test Crisis Communication messages to all employees (1Initiate & 1 Stand Down)
0% | Document Hotwash findings
0% | Collect the Sign-In Sheet, PPT w. Lessons Learned, evaluator checklist and participant survey at the conclusion of the drill.
0% | Post-Test Activities
0% | Record survey responses in the feedback spreadsheet located in the COOP Drill folder.
0% | Scan all documents into the organization folder on the shared drive and send copy/original to the agency
0% | Review evaluators' documentation
0% | Review participants' evaluations
0% | Prepare COOP AAR post-exercise report & copy DTI for Review
0% | Send Final COOP Post Exercise Report to DEMA
0% | Ensure that Plan Builders and/or Business Unit Leaders take corrective action based on AAR report
0% | Modify relocation procedures, if needed
0% | Update COOP Planbuilding Tool based on findings

## Resource_Table
% Complete | Type | Group | Email Address | Resource Responsibility | Standard Rate | Cost Per Use | Notes
0% | Business Continuity Planning |  |  |  | $0.00/h | 0
0% | Work |  |  |  | $50.00/h | 0
0% | Work |  |  |  | $50.00/h | 0
0% | Work |  |  |  | $100.00/h | 0
0% | Work |  |  |  | $70.00/h | 0
0% | Schedule meetings with agency COOP Coordinator(s) & DEMA Continuity Coordinator (DEMA As Optional) |  |  |  | $0.00/h | 0
0% | Work |  |  |  | $0.00/h | 0
0% | Work |  |  |  | $0.00/h | 0
0% | Work |  |  |  | $0.00/h | 0
0% | Work |  |  |  | $0.00/h | 0
0% | Work |  |  |  | $0.00/h | 0
0% | Schedule tour at Alternate/Drill Location (if applicable) |  |  |  | $0.00/h | 0
0% | Tour Alternate/Drill Location (if applicable) |  |  |  | $0.00/h | 0
0% | Review and confirm Alternate/Drill Location room specifications (if applicable) |  |  |  | $0.00/h | 0
0% | Review and confirm Alternate/Drill Location network/phone specifications (if applicable)
0% | Review and confirm parking availability (if applicable)
0% | Have technical resource identify necessary equipment (Laptop, Projector & Projection Screen) (if applicable)
0% | Identify both technical and basic office supplies (Flip Chart/White Board/Pens/Tablets) (if applicable)
0% | Agency Continuity Coordinator schedule date for equipment prepositioning (if applicable)
0% | Agency Continuity Coordinator ensure equipment is prepositioned at Alternate/Drill Location (if applicable)
0% | Agency Continuity Coordinator order needed supplies (if applicable)
0% | Agency Continuity Coordinator schedule equipment testing (if applicable)
0% | Technical resource conducts equipment testing (if applicable)
0% | Continuity Coordinator Document any findings from equipment testing (if applicable)
0%
0%
0%
0%
0%
0%
0%
0%
0%
0% | Conduct meeting with evaluators to review roles and responsibilities
0%
0%
0% | Solicit resources for assessment of infrastructure requirements for each location
0%
0%
0%
0% | Send courtesy invite for exercise to DEMA representatives Mike O'Malley & Edward "Tony" Lee
0% | Send courtesy invite for exercise to DTI COOP Liaison and DTI Customer Engagement Specialist
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0% | Update COOP Planbuilding Tool based on findings

## Assignment_Table
% Complete | Work | Resource Responsibility
0% | Business Continuity Planning
0% | 8h
0% | 106.4h
0% | 760h
0% | 16h
0% | Schedule meetings with agency COOP Coordinator(s) & DEMA Continuity Coordinator (DEMA As Optional)
0% | 56h
0% | 4h
0% | 80h
0% | 80h
0% | 160h
0% | Schedule tour at Alternate/Drill Location (if applicable)
0% | Tour Alternate/Drill Location (if applicable)
0% | Review and confirm Alternate/Drill Location room specifications (if applicable)
0% | Review and confirm Alternate/Drill Location network/phone specifications (if applicable)
0% | Review and confirm parking availability (if applicable)
0% | Have technical resource identify necessary equipment (Laptop, Projector & Projection Screen) (if applicable)
0% | Identify both technical and basic office supplies (Flip Chart/White Board/Pens/Tablets) (if applicable)
0% | Agency Continuity Coordinator schedule date for equipment prepositioning (if applicable)
0% | Agency Continuity Coordinator ensure equipment is prepositioned at Alternate/Drill Location (if applicable)
0% | Agency Continuity Coordinator order needed supplies (if applicable)
0% | Agency Continuity Coordinator schedule equipment testing (if applicable)
0% | Technical resource conducts equipment testing (if applicable)
0% | Continuity Coordinator Document any findings from equipment testing (if applicable)
0% | 8h
0% | 8h
0% | 8h
0% | 112h
0% | 8h
0% | 120h
0% | 157.5h
0% | 112h
0% | 160h
0% | Conduct meeting with evaluators to review roles and responsibilities
0% | 120h
0% | 4h
0% | Solicit resources for assessment of infrastructure requirements for each location
0% | 2h
0% | 2h
0% | 2h
0% | Send courtesy invite for exercise to DEMA representatives Mike O'Malley & Edward "Tony" Lee
0% | Send courtesy invite for exercise to DTI COOP Liaison and DTI Customer Engagement Specialist
0% | 2h
0% | 7.5h
0% | 60h
0% | 60h
0% | 56h
0% | 56h
0% | 200h
0% | 8h
0% | 80h
0% | 120h
0% | 200h
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0% | Update COOP Planbuilding Tool based on findings